## Budget
|  | Estimate | Spent | Remaining | Budget | 19209.34
0. | Software | 400 | 400 | 0
1. | Consulting | 0 | 0 | 0
2. | Grass and Sprinklers | 4555.9463 | 2398 | -2157.9463
3. | Mulch | 2190 | 0 | -2190
4. | Paver Patio | 4535.6 | 132 | -4403.6
5. | mother-in-law Patio | 576 | 76 | -500
6. | Walkway (Side Yard) | 3479.8 | 0 | -3479.8
7. | Walkway (Backyard) | 3364.3 | 0 | -3364.3
8. | Gate | 250 | 0 | -250
9. | Lighting | 1552 | 1144 | -408
10. | Drainage | 1313 | 1063 | -250
11. | Tools | 2408 | 1188 | -1220
12. | Ethernet/Electrical | 878 | 878 | 0
13. | Kid Labor | 1000 | 490 | -510
| Total | 26502.6463 | 7769
| Remaining | -7293.3063 | 11440.34 | -18733.6463

## 0_Software
0. Software
Description | Estimate | Date | Amount | Amount Rounded Up
Idea Spectrum Realtime Landscaping Software Architect | 400 | 2020-03-30 | 399.95 | 400
| 400 |  | Total | 400

## 1_Consulting
1. Consulting
Description | Original Estimate | Estimate | Date | Amount | Amount Rounded Up
Landscape guy | 250 | 0 |  |  | 0
|  | 0 |  | Total | 0

## 2_Grass_and_sprinkler
2. Grass and Sprinkler | [5 empty] | Calculations
[7 empty] | Grass |  | Back reed | Second tree
[6 empty] | Square footage | 715 |  | 352 | 150
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Permit |  | 34.5 |  |  | 0 | Zones regular | 5
Compost Amendment 4 cu yd/1000ft Need 3 cubic yards |  | 244.1 |  | 241.38 | 242 | Zones Drip | 4
Ground Plastic |  | 106 |  | 106 | 106
Drainage Pipe |  | 31 |  | 31 | 31 | Pipe | Main line | regular line | Drip line
EZ Drain Pipe (for Example) |  | 54 |  | 53.946 | 54 | main line | 200
6x 3/4" PVC Tee | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-PVC-Sch-40-S-x-S-Tee-PVC024000800HD/203812197 | 4 | 2020-06-22 | 3.9528 | 4 | Drip back |  | 116
3/4" PVC ball Valve | https://www.homedepot.com/p/Homewerks-Worldwide-3-4-in-PVC-Sch-40-Slip-x-Slip-Ball-Valve-VBVP40E4B/202370032 | 4 | 2020-06-22 | 3.2184 | 4 | Back Trees |  | 130
3/4 in male adapter | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Male-Adapter-C436-007/100348150 | 4 | 2020-06-22 | 3.9528 | 4 | Drip Carolyn |  | 23
3/4" brass fitting | https://www.homedepot.com/p/Everbilt-3-4-in-MHT-x-3-4-in-FIP-Brass-Adapter-Fitting-801759/300096107?keyword=887480017595&semanticToken=300300r001221000_25333d11eda3fbdb193fa117022b22de_1593355542104+300300r001221000+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B887480017595%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B887480017595%7D%3Aqu | 6 | 2020-06-22 | 5.5944 | 6 | Drip window Well |  | 55
2x 3/4" ball valve | https://www.homedepot.com/p/Everbilt-3-4-in-Lead-Free-Brass-Threaded-FPT-x-FPT-Ball-Valve-116-2-34-EB/205816051?keyword=820633959687&semanticToken=300300r001221000_d7ef2063de8c33113ab95bdcb906d8d8_1593355588523+300300r001221000+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B820633959687%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B820633959687%7D%3Aqu | 34 | 2020-06-22 | 33.048 | 34 | Line #1 (from left) |  | 69
PVC Solvent | https://www.homedepot.com/p/Oatey-8-oz-PVC-Handy-Pack-Purple-Primer-and-Solvent-Cement-302483/100151579?keyword=038753302485&semanticToken=d00300r011221000_51e3b4cfae674eb36b6f28079ba35b1b_1593355676733+d00300r011221000+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B038753302485%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B038753302485%7D%3Aqu | 9 | 2020-06-22 | 8.6076 | 9 | Line #2 |  | 71
3/4" PVC socket | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-PVC-Coupling-Socket-x-Socket-50-Pack-PVC-02100-0850HD/307851979 | 12 | 2020-06-22 | 11.8584 | 12 | Line #3 |  | 35
3/4" PVC 90 deg pack | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-PVC-90-Degree-Elbow-Socket-x-Socket-35-Pack-PVC-02300-0835HD/307852036 | 12 | 2020-06-22 | 11.8584 | 12 | Line #4 |  | 46
3/4" PVC 45 deg pack | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-PVC-Elbow-SxS-20-Pack-PVC-02309-0820HD/307852172 | 12 | 2020-06-22 | 11.8584 | 12 | Line #5 |  | 32
10x 3/4" PVC sch 40 10ft | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-10-ft-PVC-Schedule-40-Plain-End-DWV-Pipe-PVC-04007-0600/100348472 | 21 | 2020-06-22 | 20.84 | 21
2x PVC cross | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-PVC-Sch-40-S-x-S-x-S-x-S-Cross-PVC024100600HD/203812455 | 6 | 2020-06-05 | 5.7672 | 6 | Totals | 200 | 577 | 0
3/4" 45deg PVC | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-45-Degree-Elbow-C417-007/100346876 | 3 | 2020-06-06 | 2.4624 | 3
3/4" PVC Cap | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Cap-C447-007/100345011 | 2 | 2020-06-07 | 1.3824 | 2 |  |  | 777
4x 3/4 PVC Plug | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Plug-C450-007/100343628 | 7 | 2020-06-08 | 6.6528 | 7 | Sprinkler heads
2x 3/4" PVC Tee | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Tee-C402-007/100347255 | 3 | 2020-06-09 | 2.1168 | 3
8x 3/4" Male Adapter | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Male-Adapter-C436-007/100348150 | 6 | 2020-06-10 | 5.2704 | 6 | Rotary | 2
2x 3/4" PVC Cap | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Cap-C448-007/100345647 | 3 | 2020-06-11 | 2.4624 | 3 | Pop ups | 19
3/4" PVC 90 def elbow | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-90-Degree-Elbow-C410-007/100344758?keyword=049081141684&semanticToken=300300r001221000_762b7395285015eeff5597ae80a5521a_1593361216779+300300r001221000+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B049081141684%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B049081141684%7D%3Aqu | 2 | 2020-06-12 | 1.2312 | 2
3x 3/4 Ball Valve | https://www.homedepot.com/p/Everbilt-3-4-in-Lead-Free-Brass-Threaded-FPT-x-FPT-Ball-Valve-116-2-34-EB/205816051 | 50 | 2020-06-13 | 49.572 | 50
3/4" Iron TEE | https://www.homedepot.com/p/LDR-Industries-3-4-in-Galvanized-Iron-Tee-313-T-34/100560785 | 5 | 2020-06-14 | 4.2768 | 5
3/4" Brass Garden Valve | https://www.homedepot.com/p/Everbilt-3-4-in-Brass-FHT-x-MHT-Garden-Valve-VGRBNOB4EB/205812113 | 13 | 2020-06-15 | 12.582 | 13
3/4" Galvanized Steel pipe | https://www.homedepot.com/p/VPC-3-4-in-x-18-in-Galvanized-Steel-Schedule-40-Cut-Pipe-22-727518/304751933 | 11 | 2020-06-16 | 10.5516 | 11
3/4" Pressure Gauge | https://www.homedepot.com/p/Watts-3-4-in-Plastic-Water-Pressure-Test-Gauge-DP-IWTG/100175467 | 11 | 2020-06-17 | 10.7784 | 11
RETURN OF 3/4 stuff |  | -189.12 |  | -189.12 | -190
Sprinkler Valve Box | https://www.homedepot.com/p/NDS-10-in-Circular-Valve-Box-111BC/100037622 | 15 | 2020-07-02 | 14.02 | 15
Jumbo Valve Box | https://www.homedepot.com/p/NDS-13-in-x-20-in-Standard-Jumbo-Valve-Box-with-ICV-Overlapping-Cover-117BC/100377391 | 39 | 2020-07-02 | 38.23 | 39
1"X10' PVC Pipe | https://www.homedepot.com/p/1-in-x-10-ft-PVC-Schedule-40-Plain-End-Pipe-531194/202280936 | 31 | 2020-07-02 | 30.46 | 31
Tee Pack https://www.homedepot.com/p/Charlotte-Pipe-1-in-SxSxS-PVC-Tee-10-Pack-PVC-02400-1010HD/307852210 90 deg elbow https://www.homedepot.com/p/Charlotte-Pipe-1-SCH-90-Degree-Elbow-Socket-x-Socket-15-Pack-PVC023001015HD/311317449 coupling https://www.homedepot.com/p/Charlotte-Pipe-1-in-PVC-Sch-40-Coupling-SxS-25-Pack-PVC-02100-1025HD/307851996 1" PVC Male Adapter https://www.homedepot.com/p/1-in-Schedule-40-PVC-Male-Adapter-C436-010/100344011 1 x 1/3/4 PVC reducing https://www.homedepot.com/p/1-in-x-3-4-in-Sch-40-PVC-Reducing-Male-Adapter-C436-131/100343192 1" Cap https://www.homedepot.com/p/1-in-Schedule-40-PVC-Cap-C447-010/100347518 3/4" by 1" https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-1-in-PVC-Sch-40-MPT-x-S-Reducer-Male-Adapter-PVC-02110-0700HD/203825614 3/4" plug https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Plug-C450-007/100343628 1in Tee https://www.homedepot.com/p/1-in-x-1-in-x-3-4-in-Schedule-40-PVC-Reducing-Tee-C402-131/100344816 3/4" female adapter https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Female-Adapter-C435-007/100345266 1" - 3/4" Tee https://www.homedepot.com/p/1-in-x-1-in-x-3-4-in-Schedule-40-PVC-Reducing-Tee-C401-131/100345365 45 deg bend https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-45-Degree-Elbow-C417-007/100346876 Plumbers tape 3/4" by 1" male adapter https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-1-in-PVC-Sch-40-MPT-x-S-Reducer-Male-Adapter-PVC-02110-0700HD/203825614 socket Elbow https://www.homedepot.com/p/Charlotte-Pipe-1-in-PVC-Side-Outlet-90-Degree-Socket-Elbow-PVC-02510-1000/309215012 Brass fitting https://www.homedepot.com/p/Everbilt-3-4-in-MHT-x-3-4-in-FIP-Brass-Adapter-Fitting-801759/300096107 |  | 92 | 2020-07-02 | 91.51 | 92
1" Brass Valve | https://www.homedepot.com/p/Apollo-1-in-Lead-Free-Brass-FNPT-x-FNPT-Full-Port-Ball-Valve-94ALF10501A/305975196 | 135 | 2020-07-02 | 134.84 | 135
Rainbird rotor https://www.homedepot.com/p/Rain-Bird-CP-3504-Part-Circle-Rotor-CP-3504-PC/203209338 Swing Arm https://www.homedepot.com/p/Rain-Bird-6-in-x-1-2-in-x-3-4-in-Swing-Pipe-Assembly-SA65/203258176 |  | 14.52 | 2020-07-02 | 14.52 | 15
Rain Bird 22SAF Mini Rotary Pop-Up Spray, | https://www.amazon.com/gp/product/B000VHE8RS/ | 18 | 2020-07-02 | 17.64 | 18
Return Brass Fitting |  | -5.59 | 2020-07-02 | -5.59 | -6
1" male Adapter https://www.homedepot.com/p/1-in-Schedule-40-PVC-Male-Adapter-C436-010/100344011 1" Cross https://www.homedepot.com/p/Charlotte-Pipe-1-in-PVC-Sch-40-S-x-S-x-S-x-S-Cross-PVC024100800HD/203812457 45 Elbow https://www.homedepot.com/p/1-in-Schedule-40-PVC-45-Degree-Elbow-C417-010/100345015 1" x 3/4 pvc https://www.homedepot.com/p/Charlotte-Pipe-1-in-x-3-4-in-PVC-Sch-40-S-x-FPT-Reducer-Female-Adapter-PVC-02101-3800HD/203824436 1 x 3/4 male https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-1-in-PVC-Sch-40-MPT-x-S-Reducer-Male-Adapter-PVC-02110-0700HD/203825614 |  | 22 | 2020-07-03 | 21.45 | 22
Brass Fitting | https://www.homedepot.com/p/Everbilt-3-4-in-FHT-x-3-4-in-FIP-Brass-Adapter-Fitting-801749/300096258 | 8 | 2020-07-03 | 7.05 | 8
4" Sprinkler https://www.homedepot.com/p/Rain-Bird-Adjustable-Pattern-4-in-Pop-Up-Spray-Head-1804AP-25/100167622 6" Swing arm https://www.homedepot.com/p/Rain-Bird-6-in-x-1-2-in-x-1-2-in-Swing-Assembly-SA5S/100141993 |  | 9 | 2020-07-03 | 8.04 | 9
Rainbird sprinkler 1804HEVNPR | https://www.homedepot.com/p/Rain-Bird-1800-Series-4-in-Pressure-Regulated-High-Efficiency-Spray-1804HEVNPR/206617992 | 8.61 | 2020-07-03 | 8.61 | 9
Manifold Tee 1" | https://sprinklersupplystore.com/products/dura-010-manifold-tee | 59.54 | 2020-07-03 | 59.54 | 60
1" x 10' PVC pipe | https://www.homedepot.com/p/1-in-x-10-ft-PVC-Schedule-40-Plain-End-Pipe-531194/202280936 | 60.91 | 2020-07-04 | 60.91 | 61
1" Brass Ball valve | https://www.homedepot.com/p/Apollo-1-in-Lead-Free-Brass-FNPT-x-FNPT-Full-Port-Ball-Valve-94ALF10501A/305975196 | 80.9 | 2020-07-04 | 80.9 | 81
PVC Glue | https://www.homedepot.com/p/Oatey-8-oz-PVC-Handy-Pack-Purple-Primer-and-Solvent-Cement-302483/100151579 | 8.61 | 2020-07-04 | 8.61 | 9
1" PVC Male Adapter https://www.homedepot.com/p/1-in-Schedule-40-PVC-Male-Adapter-C436-010/100344011 PTFE TAPE 1-1/4" 90 Deg PVC https://www.homedepot.com/p/Carlon-1-1-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AGB-CTN/202303990 3/4" galvanized Tube Straps https://www.homedepot.com/p/Oatey-3-4-in-Galvanized-Tube-Strap-2-Hole-10-Pack-33543/303434704 3/4" PVC Cap https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Cap-C448-007/100345647 3/4" by 1" male adapter https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-1-in-PVC-Sch-40-MPT-x-S-Reducer-Male-Adapter-PVC-02110-0700HD/203825614 1" PVC 25 pack https://www.homedepot.com/p/Charlotte-Pipe-1-in-PVC-Sch-40-Coupling-SxS-25-Pack-PVC-02100-1025HD/307851996 1" PVC Cap https://www.homedepot.com/p/1-in-Schedule-40-PVC-Cap-C447-010/100347518?keyword=049081136826 |  | 34.96 | 2020-07-04 | 34.96 | 35
500' 18/10 sprinkler wire | https://www.homedepot.com/p/Southwire-500-ft-18-10-Black-Solid-UL-Burial-Sprinkler-System-Wire-49270245/202316416 | 336.71 | 2020-07-06 | 336.71 | 337
Rainbird ESPME3 controller | https://www.amazon.com/gp/product/B07RM8W33F/ | 346.4 | 2020-07-07 | 346.4 | 347
13x Rainbird valve 100-HV-NPT | https://sprinklersupplystore.com/products/100-hv-npt-rainbird-1-26-34-fxf-valve | 188.6 | 2020-07-10 | 188.6 | 189
waterproof direct burial | https://www.amazon.com/gp/product/B07D538F86 | 71 | 2020-07-21 | 70.18 | 71
PVC pipe tc | https://www.homedepot.com/p/3-4-in-Schedule-40-PVC-Plug-C450-007/100343628 https://www.homedepot.com/p/Grease-Cap-with-Orange-Nut-25-Pack-57505W/100195778 | 262 | 2020-07-24 | 261.03 | 262
s | https://www.homedepot.com/p/Vigoro-4-in-Weed-Barrier-Landscape-Fabric-Garden-Staples-500-Pack-8500RV/302720136 | 43.18 | 2020-08-02 | 43.18 | 44
PVC Parts |  | 31.5 | 2020-08-02 | 31.5 | 32
800' Pipe @10ft | https://www.homedepot.com/p/Charlotte-Pipe-3-4-in-x-10-ft-PVC-Schedule-40-Plain-End-DWV-Pipe-PVC-04007-0600/100348472 | 166.752 |  |  | 0
Drip lines |  | 50 |  |  | 0
2x 4" rotary 22SA-RVAN | https://www.amazon.com/Rain-Bird-22SA-RVAN-Rotary-Adjustable/dp/B00HN7P3AA/ref=sr_1_7?dchild=1&keywords=rainbird+6%22+pop+up&qid=1590104623&sr=8-7 | 25 |  |  | 0
16x pop up 1800 series | https://www.homedepot.com/p/Rain-Bird-1800-Series-4-in-Pressure-Regulated-High-Efficiency-Spray-1804HEVNPR/206617992 https://www.amazon.com/Rain-Bird-Professional-Sprinkler-Adjustable/dp/B081LFJWP8/ | 128 |  |  | 0
16 x swing pipes | https://www.homedepot.com/p/Rain-Bird-6-in-x-1-2-in-x-3-4-in-Swing-Pipe-Assembly-SA65/203258176 | 48 |  |  | 0
valve box |  | 30 |  |  | 0
Paver border (150') | https://www.homedepot.com/p/ProFlex-48-ft-Paver-Edging-Project-Kit-in-Black-1260HD-48C/203720013 | 174.9 |  |  | 0
Paver edging | https://www.homedepot.com/p/Pavestone-RumbleStone-Rec-10-5-in-x-7-in-x-1-75-in-Cafe-Concrete-Paver-90969/203647574 | 565.7143 |  |  | 0
Sod |  | 536.25 |  |  | 0
0
Misc |  | 400 |  |  | 0
0
|  | 4555.9463 |  | Total | 2398
Note on D7: Windows User: Delivery $89 $47/cubic yd + tax

## 3_Mulch
3. Mulch | [5 empty] | Calculations
Grass
[6 empty] | North Side | 600
Description | URLS | Estimate | Date | Amount | Amount Rounded Up | South Side | 800
Mulch |  | 1640 |  |  | 0 | Back Side | 350
1x Baby Blue Spruce Tree |  | 250 |  |  | 0 | Carolyn Patio | 30
3x low bushes |  | 150 |  |  | 0 | Stairs Bed | 110
10x Feather Reed Grass |  | 150 |  |  | 0 | Near Patio | 100
[6 empty] | Total | 1990
|  | 2190 |  | Total | 0
[6 empty] | Cubic yards needed | 20
1 cu yd cover 100 sq ft

## 4_Paver_Patio
4. Paver Patio | [6 empty] | Calculations
Grass
[7 empty] | sq ft | 300
Description | URLS | Original Estimate | Estimate | Date | Amount | Amount Rounded Up
Paver Examples |  |  | 29 |  | 29 | 29
Ewing hardscape Paver examples |  |  | 60 | 2020-06-11 | 56.43 | 57
Ewing hardscape Paver examples |  |  | 26.99 | 2020-06-12 | 26.99 | 27
C&C SAND & STONE-SITEONCASTLE ROCK COUS |  |  | 30 | 2020-06-12 | 13.36 | 14
Home Depot Pavers |  |  | 5 | 2020-06-12 | 4.18 | 5
Gray Breeze Gravel (4 inches of base) |  |  | 419 |  |  | 0
Mason Sand (1" deep) |  |  | 116.6 |  |  | 0
Pavers center | https://unilock.com/product/beacon-hill-smooth-chicago/ |  | 3600 |  |  | 0
Perma Sand | https://www.homedepot.com/p/SAKRETE-PermaSand-40-lb-Paver-Joint-Sand-65470004/202070568 |  | 250 |  |  | 0
Wall Bench |  | 1200 |  |  |  | 0
Firepit |  | 800 |  |  |  | 0
Sand compactor rental |  |  | 150 |  |  | 0
|  |  | 4535.6 |  | Total | 132

## 5_mother-in-law_Patio
5. Carolyn Patio | [6 empty] | Calculations
Grass
[7 empty] | sq ft | 110
Description | URLS | Original Estimate | Estimate | Date | Amount | Amount Rounded Up
Concrete Drill bit | https://www.homedepot.com/p/Tapcon-3-16-in-x-5-1-2-in-Carbide-Tipped-Masonery-Drill-Bit-11362/100166555 |  | 7 | 2020-06-12 | 6.45 | 7
Concrete Drills | https://www.homedepot.com/p/Tapcon-1-4-in-x-2-3-4-in-Hex-Washer-Head-Concrete-Anchors-25-Pack-24230/100114651 |  | 16 | 2020-06-12 | 15.1 | 16
Wood and pavers for stairs | https://www.homedepot.com/p/2-in-x-12-in-x-8-ft-Premium-2-and-Better-Douglas-Fir-Lumber-707195/202094201 https://www.homedepot.com/p/Pavestone-Taverna-Rec-12-in-x-8-in-x-2-in-Eddington-Blend-Concrete-Paver-25329/303540931 |  | 43 | 2020-06-14 | 42.14 | 43
Pavers for stairs | https://www.homedepot.com/p/Pavestone-Taverna-Rec-12-in-x-8-in-x-2-in-Eddington-Blend-Concrete-Paver-25329/303540931 |  | 10 | 2020-06-14 | 9.42 | 10
Wood for staires |  |  | 500 |  |  | 0
Pavers center |  | 1680
Stairs |  | 1000 |  |  |  | 0
|  |  | 576 |  | Total | 76

## 6_walkway_side_yard
6. Walkway Side Yard | [5 empty] | Calculations
Grass
[6 empty] | sq ft | 275
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Gray Breeze Gravel (4 inches of base) |  | 391.5 |  |  | 0
Mason Sand (1" deep) |  | 58.3 |  |  | 0
Pavers center |  | 2160 |  |  | 0
Pavers border |  | 720 |  |  | 0
Sand compactor rental |  | 150 |  |  | 0
|  | 3479.8 |  | Total | 0

## 7_walkway_back_yard
7. Walkway Back Yard | [5 empty] | Calculations
Grass
[6 empty] | sq ft | 170
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Gray Breeze Gravel (4 inches of base) |  | 276 |  |  | 0
Mason Sand (1" deep) |  | 58.3 |  |  | 0
Pavers center |  | 2160 |  |  | 0
Pavers border |  | 720 |  |  | 0
Sand compactor rental |  | 150 |  |  | 0
|  | 3364.3 |  | Total | 0

## 8_Gate
8. Gate
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Gate |  | 250 |  |  | 0
|  | 250 |  | Total | 0

## 9_lighting
9. Lighting | [5 empty] | Calculations
length
[6 empty] | Front path | 250
Description | URLS | Estimate | Date | Amount | Amount Rounded Up | Side Path | 100
Electrical outlet and wall panel |  | 11 | 2020-05-30 | 11 | 11 | Back | 156
Power Controller | https://www.amazon.com/dp/B06X1D267N/ | 118 | 2020-06-14 | 117.69 | 118 | Carolyn Porch + | 95
Low voltage light 3 Watt | https://www.lowes.com/pd/Kichler-3-Watt-Olde-Bronze-Low-Voltage-Hardwired-LED-Path-Light/1000191807 | 47 | 2020-06-13 | 46.96 | 47
12/2 wire | https://www.homedepot.com/p/Southwire-75-ft-12-2-Black-Stranded-CU-Low-Voltage-Landscape-Lighting-Wire-55213446/308403406 | 47 | 2020-06-14 | 46.99 | 47
Stair Light | https://www.lowes.com/pd/Portfolio-2-Watt-Specialty-Textured-Bronze-Low-Voltage-Low-Voltage-LED-Step-Light/999928462 | 19 | 2020-06-14 | 18.34 | 19
Southwire 12-2 Landscape Lighting Cable 500 ft. | https://www.amazon.com/gp/product/B00HO02GPQ/ https://www.homedepot.com/p/Southwire-500-ft-12-2-Black-Stranded-CU-Low-Voltage-Landscape-Lighting-Wire-55213445/202316307 | 193 | 2020-06-18 | 192.61 | 193 |  | 601
5x Low voltage light 3 Watt | https://www.lowes.com/pd/Kichler-3-Watt-Olde-Bronze-Low-Voltage-Hardwired-LED-Path-Light/1000191807 | 235 | 2020-06-18 | 234.79 | 235
5x Low voltage light 3 Watt and 2 Watt bulb | https://www.lowes.com/pd/Kichler-3-Watt-Olde-Bronze-Low-Voltage-Hardwired-LED-Path-Light/1000191807 | 248 | 2020-06-24 | 247.97 | 248
500' https://www.wireandcableyourway.com/12-2c-landscape-lighting-cable.html | https://www.amazon.com/gp/product/B00HO02GPQ/ https://www.homedepot.com/p/Southwire-500-ft-12-2-Black-Stranded-CU-Low-Voltage-Landscape-Lighting-Wire-55213445/202316307 | 193 | 2020-06-28 | 192.61 | 193
1-1/4 90 deg PVC https://www.homedepot.com/p/Charlotte-Pipe-1-1-4-in-PVC-Sch-40-90-Degree-S-x-S-Elbow-PVC023001200HD/203812127 Extension Cord https://www.homedepot.com/p/HDX-15-ft-16-3-Indoor-Tight-Space-Cube-Tap-Extension-Cord-White-HD-433-950/202529045 1-1/4 galvanized Tube https://www.homedepot.com/p/Oatey-1-1-4-in-Galvanized-Tube-Strap-2-Hole-4-Pack-33545/303434700 1-1/4" x 10' PVC https://www.homedepot.com/p/1-1-4-in-x-10-ft-PVC-Sch-40-DWV-Plain-End-Pipe-1586/100147742 |  | 27 | 2020-07-06 | 26.97 | 27
1-1/4" x 10' PVC Pipe | https://www.homedepot.com/p/1-1-4-in-x-10-ft-PVC-Sch-40-DWV-Plain-End-Pipe-1586/100147742 | 6 | 2020-07-08 | 5.26 | 6
4 Lamps | https://www.lowes.com/pd/Portfolio-4-Watt-Powder-Coated-Bronze-Low-Voltage-LED-Path-Light/999928438 | 188 |  |  | 0
2 Spotlights | https://www.lowes.com/pd/Portfolio-182-Lumen-4-5-Watt-Specialty-Textured-Bronze-Low-Voltage-LED-Landscape-Flood-Light/50295269 | 110 |  |  | 0
Stair Lights | https://www.homedepot.com/p/Hampton-Bay-Black-Integrated-LED-Deck-Light-JAO2601L/301610345 | 110
|  | 1552 |  | Total | 1144

## 10. Drainage
10. Drainage | [5 empty] | Calculations
Grass
[6 empty] | North Side | 77
Description | URLS | Estimate | Date | Amount | Amount Rounded Up | South Side | 76
Snap drain coupling | https://www.acehardware.com/departments/plumbing/pipe-fittings/plastic-fittings/4807996 | 10 |  | 9.91 | 10 | Back | 75
12" Basin | https://www.homedepot.com/p/NDS-12-in-x-12-in-Drainage-Catch-Basin-2-Opening-Kit-1200BKIT/100377423?MERCH=REC-_-plpsearch_multi-_-NA-_-100377423-_-N | 56 |  | 55.47 | 56 | Porch Front | 34
12" Basin | https://www.homedepot.com/p/NDS-12-in-x-12-in-Drainage-Catch-Basin-2-Opening-Kit-1200BKIT/100377423?MERCH=REC-_-plpsearch_multi-_-NA-_-100377423-_-N | 56 |  | 55.47 | 56 | Carolyn Porch | 34
12" Platic Drainage Square | https://www.homedepot.com/p/NDS-12-in-Plastic-Square-Drainage-Catch-Basin-Grate-with-Wave-Design-in-Green-1224GRRTL/204798934?keyword=052063057576&semanticToken=300300r00122100_b3b479eaab6f866dba7537e7871a56ee_1592221542778+300300r00122100+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B052063057576%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B052063057576%7D%3Aqu | 29 |  | 28.31 | 29
EZ Drain | https://www.homedepot.com/p/NDS-3-in-x-10-ft-EZ-Drain-Prefabricated-French-Drain-with-Pipe-EZ-0702F/203477913 | 54 |  | 53.95 | 54
3 different drain end types |  | 10 |  | 9.36 | 10 | total | 296
12" Basin | https://www.homedepot.com/p/NDS-12-in-x-12-in-Drainage-Catch-Basin-2-Opening-Kit-1200BKIT/100377423?MERCH=REC-_-plpsearch_multi-_-NA-_-100377423-_-N | 56 | 2020-06-19 | 55.47 | 56
2x EZ Drain | https://www.homedepot.com/p/NDS-3-in-x-10-ft-EZ-Drain-Prefabricated-French-Drain-with-Pipe-EZ-0702F/203477913 | 108 | 2020-06-22 | 107.89 | 108
3x Caulk | https://www.homedepot.com/p/DAP-Alex-Plus-10-1-oz-White-Acrylic-Latex-Caulk-Plus-Silicone-18103/100097524 | 9 | 2020-06-22 | 8.36 | 9 | Required | 30
2x Caps | https://www.homedepot.com/p/NDS-4-in-PVC-Sewer-and-Drain-Cap-4P06/100172701 | 6 | 2020-06-22 | 5.01 | 6
6x 3" snap Coupler | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-Polyethylene-Slip-External-Snap-Coupler-0312AA/100568058 | 15 | 2020-06-22 | 14.64 | 15
12" Catch Basin | https://www.homedepot.com/p/NDS-12-in-x-12-in-Drainage-Catch-Basin-2-Opening-Kit-1200BKIT/100377423?MERCH=REC-_-plpsearch_multi-_-NA-_-100377423-_-N | 56 | 2020-06-22 | 55.47 | 56
5x 10' 3" corrugated drain pipes | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-x-10-ft-Corrugated-Pipes-Drain-Pipe-Solid-03540010/202522641?keyword=096942631877&semanticToken=300300r001221000_1bc6c7683957fd31643c49a77cb5b8e9_1593357360283+300300r001221000+%3E++cnn%3A%7B14%3A0%7D+cnr%3A%7B7%3A0%7D+cnp%3A%7B10%3A0%7D+cnd%3A%7B4%3A0%7D+cne%3A%7B8%3A0%7D+cnb%3A%7B0%3A0%7D+cns%3A%7B5%3A0%7D+cnx%3A%7B3%3A0%7D+cnq%3A%7B0%3A0%7D+cnw%3A%7B0%3A0%7D+cnv%3A%7B0%3A0%7D+st%3A%7B096942631877%7D%3Ast+oos%3A%7B0%3A1%7D+tgr%3A%7BNo+stage+info%7D+smf%3A%7Bca%2Cbr%7D%3Asmf+nf%3A%7B1%7D%3Anf+qu%3A%7B096942631877%7D%3Aqu | 41 | 2020-06-22 | 40.99 | 41
4x Mitered Drains | https://drainageproducts.us/3-pvc-sch-40-mitered-drain-w-brown-hdpe-grate/ | 139 | 2020-06-23 | 138.58 | 139
4' Tall stakes | https://www.homedepot.com/p/1-in-x-2-in-x-48-in-Grade-Stakes-12-Pieces-462633/202090640 | 17 | 2020-06-23 | 16.63 | 17
NDS cap for Drain | https://www.amazon.com/gp/product/B000BOB7O8 https://www.acehardware.com/departments/plumbing/parts-and-repair/catch-basins-and-covers/4865820 | 53 | 2020-06-25 | 52.5 | 53
3x 3" ABS CAP | https://www.homedepot.com/p/NIBCO-3-in-ABS-DWV-Hub-Cap-C5817HD3/204700370 | 15 | 2020-06-25 | 14.19 | 15
2x EZ Drain | https://www.homedepot.com/p/NDS-3-in-x-10-ft-EZ-Drain-Prefabricated-French-Drain-with-Pipe-EZ-0702F/203477913 | 108 | 2020-06-25 | 107.89 | 108
4x 3" Drain pipe | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-x-10-ft-Corrugated-Pipes-Drain-Pipe-Solid-03540010/202522641 | 33 | 2020-06-25 | 32.79 | 33
12" Basin | https://www.homedepot.com/p/NDS-12-in-x-12-in-Drainage-Catch-Basin-2-Opening-Kit-1200BKIT/100377423 | 56 | 2020-06-26 | 55.4688 | 56
Hand Pump | https://www.homedepot.com/p/VPC-Pump-A-Way-Manual-Non-Submersible-Hand-Pump-9136/202277592 | 33 | 2020-06-26 | 32.346 | 33
3" solid end cap | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-Solid-Snap-End-Cap-0332AA/100541009 | 5 | 2020-06-26 | 4.9572 | 5
3" slip wye | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-Polyethylene-Slip-Wye-0322AA/100562986 | 8 | 2020-06-26 | 7.3224 | 8
10x Drainage Pipe | https://www.homedepot.com/p/Advanced-Drainage-Systems-3-in-x-10-ft-Corrugated-Pipes-Drain-Pipe-Solid-03540010/202522641 | 82 | 2020-06-26 | 81.972 | 82
3" by 3" PVC coupling | https://www.homedepot.com/p/Fernco-3-in-x-3-in-PVC-DWV-Mechanical-Flexible-Coupling-P1056-33/100372296 | 8 | 2020-07-04 | 7.32 | 8
More Drain pipe |  | 100 |  |  | 0
Misc Couplers and outlet/rock at end |  | 150 |  |  | 0
|  | 1313 |  | Total | 1063

## 11. Tools
11. Tools
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Razor Back Shovel |  | 33 | 2020-05-20 | 32.38 | 33
Razor Back rakes |  | 63 | 2020-05-21 | 62.6 | 63
Jun Joe TJ603 Tiller | https://www.amazon.com/gp/product/B00V6IEVXM/ref=ppx_yo_dt_b_asin_title_o00_s00?ie=UTF8&psc=1 | 142 | 2020-05-21 | 141.22 | 142
Arc Thrift Store Patio Book |  | 3 | 2020-05-23 | 2.16 | 3
Gloves |  | 55 | 1930-05-23 | 55 | 55
Wheel barrow | https://www.homedepot.com/p/Jackson-6-cu-ft-Heavy-Gauge-Seamless-Steel-Wheelbarrow-with-Total-Control-Handles-M6TC14/206205191 | 135 | 2020-05-23 | 135 | 135
Razor back pick ax |  | 51 | 2020-05-30 | 50.12 | 51
100' Measuring Tape |  | 23 | 2020-05-31 | 23 | 23
Electrical Tape and wall mounts |  | 18 | 2020-05-31 | 18 | 18
Garden Hoe, 8x8 Steel tamper |  | 54 | 2020-06-01 | 53.9568 | 54
Level | https://www.homedepot.com/p/Empire-True-Blue-12-in-Magnetic-Tool-Box-Level-EM81-12/100081706 | 14 | 2020-06-05 | 13.46 | 14
Dewalt Drill | https://www.homedepot.com/p/DEWALT-20-Volt-MAX-XR-Lithium-Ion-Brushless-Cordless-1-2-in-Drill-Driver-with-5-Ah-Battery-Charger-and-Tool-Bag-DCD791P1/312119566 | 323 | 2020-06-12 | 322.92 | 323
5 Gallon Cooler | https://www.lowes.com/pd/Igloo-5-Gallon-Beverage-Cooler/999949202 | 27 | 2020-06-13 | 26.98 | 27
Maxfit 60 piece tool set | https://www.homedepot.com/p/DEWALT-MAXFIT-Screwdriving-Set-60-Piece-DWAMF60/308249340 | 27 | 2020-06-14 | 26.97 | 27
Pipe Cutter | https://www.amazon.com/gp/product/B001HWQAI6/ | 60 | 2020-06-19 | 59.49 | 60
Hole Dozer Saw Set Pack | https://www.homedepot.com/p/Milwaukee-Hole-Dozer-General-Purpose-Bi-Metal-Hole-Saw-Set-13-Piece-49-22-4025/202327772 | 92 | 2020-07-04 | 91.77 | 92
1/4 x 12" Drill Bit https://www.homedepot.com/p/DEWALT-1-4-in-x-12-in-Black-and-Gold-Drill-Bit-DW1606-G/202579645 12" x 3/8 Extension https://www.homedepot.com/p/Milwaukee-12-in-x-3-8-in-Bit-Extension-for-Selfeed-Bits-and-Hole-Saws-48-28-4008/202256266 1-1/8 hole dozer https://www.homedepot.com/p/Milwaukee-1-1-8-in-Hole-Dozer-Bi-Metal-Hole-Saw-49-56-9611/202327745 1-3/4 hole https://www.homedepot.com/p/Milwaukee-1-3-4-in-Hole-Dozer-Bi-Metal-Hole-Saw-49-56-9621/202327749 |  | 68 | 2020-07-06 | 67.85 | 68
Hand tools |  | 300 |  |  | 0
Dewalt Wet saw | https://www.homedepot.com/p/DEWALT-10-in-Wet-Tile-Saw-with-Stand-D24000S/203054774 | 920 |  |  | 0
0
0
0
0
|  | 2408 |  | Total | 1188

## 12. Ethernet
12. Ethernet/Electrical
Runs
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Conduit | https://www.homedepot.com/p/JM-eagle-3-4-in-x-10-ft-PVC-Schedule-40-Conduit-67454/100129197 | 32 | 2020-06-19 | 31.53 | 32 | 1 | 110
Misc conduit pipe stuff | https://www.homedepot.com/p/TAYMAC-2-Gang-Weatherproof-Extra-Duty-In-Use-Clear-Cover-MM2420C/302212637 https://www.homedepot.com/p/BELL-1-2-in-Gray-Weatherproof-Closure-Plug-4-Pack-5269-0B/204208004 https://www.homedepot.com/p/BELL-Gray-2-Gang-Weatherproof-Box-with-Three-1-2-in-Threaded-Outlets-5333-0B/204208017 https://www.homedepot.com/p/BELL-Gray-2-Gang-Weatherproof-Box-with-Three-1-2-in-Threaded-Outlets-5333-0B/204208017 https://www.homedepot.com/p/3-4-in-Male-Terminal-Adapter-R5140104/202043511 https://www.homedepot.com/p/Carlon-3-4-in-45-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA7AEB-CTN/100404150 https://www.homedepot.com/p/Carlon-3-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AEB-CTN/202304074 https://www.homedepot.com/p/Oatey-8-oz-PVC-Electrical-Solvent-Cement-Gray-31040/206751887 | 68 | 2020-06-19 | 68 | 68
250ft 12/3 wire | https://www.homedepot.com/p/Southwire-250-ft-12-3-Gray-Solid-CU-UF-B-W-G-Wire-13058355/202316479 | 167 | 2020-06-19 | 166.48 | 167 | 2 | 65
1000' cat6 outdoor (burial) | https://www.cablewholesale.com/products/network-phone/cat-6-cable-bulk/product-10x8-622nh.php https://www.amazon.com/gp/product/B005AIP8Z4/ | 250 | 2020-06-19 | 250 | 250
Amcrest POE camera | https://www.amazon.com/gp/product/B083G9KT4C/ | 66 | 2020-06-19 | 66 | 66
2x 2-gang weatherproof box | https://www.homedepot.com/p/BELL-2-Gang-Weatherproof-Box-with-Three-3-4-in-Outlets-5341-0B/204208020 | 23 | 2020-06-22 | 22.33 | 23
GFCI | https://www.homedepot.com/p/Leviton-15-Amp-Self-Test-SmartlockPro-Slim-Duplex-GFCI-Outlet-White-R72-GFNT1-0RW/205996720 | 18 | 2020-06-22 | 17.02 | 18
2x GFCI Weather Resistance | https://www.homedepot.com/p/Leviton-15-Amp-125-Volt-Duplex-Self-Test-Tamper-Resistant-Weather-Resistant-GFCI-Outlet-White-R92-GFWT1-0KW/205996792 | 47 | 2020-06-22 | 46.72 | 47
1 - 1/4" x 10ft PVC Conduit | https://www.homedepot.com/p/JM-eagle-1-1-4-in-x-10-ft-PVC-Schedule-40-Conduit-67470/100196693 | 7 | 2020-07-04 | 6.7 | 7
3/4" 90 deg bend | https://www.homedepot.com/p/Carlon-3-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AEB-CTN/202304074 | 2 | 2020-07-04 | 1.02 | 2
6ft 13 amp 3-prong | https://www.homedepot.com/p/HDX-6-ft-13-Amp-3-Prong-Grey-Appliance-Replacement-Cord-HD-588-547/100672804 | 20 | 2020-07-06 | 19.38 | 20
3/4" 90 deg elbow | https://www.homedepot.com/p/Carlon-3-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AEB-CTN/202304074 | 3 | 2020-07-08 | 2.03 | 3
12x 3/4" x 10ft conduit | https://www.homedepot.com/p/JM-eagle-3-4-in-x-10-ft-PVC-Schedule-40-Conduit-67454/100129197 | 33 | 2020-07-08 | 32.16 | 33
2x Ethernet Wall Plate | https://www.homedepot.com/p/Commercial-Electric-2-Port-Decor-Data-Wall-Plate-Insert-White-5152-WH/206427829 | 9 | 2020-07-11 | 8.25 | 9
Saw Blade | https://www.homedepot.com/p/DIABLO-4-in-x-6-TPI-Fast-and-Wood-Bi-Metal-Jigsaw-Blade-5-Pack-DJT101DF5/313114938 | 15 | 2020-07-11 | 14.01 | 15
PVC electrical solvent Gray | https://www.homedepot.com/p/16-oz-PVC-Electrical-Solvent-Cement-Gray-31041/206751903 | 8 | 2020-07-11 | 7.41 | 8
2x 1-1/4 x 3/4 PVC reducer Bushing | https://www.homedepot.com/p/Charlotte-Pipe-1-1-4-in-x-3-4-in-PVC-Sch-40-SPG-x-S-Reducer-Bushing-PVC021070950HD/203811453 | 3 | 2020-07-11 | 2.46 | 3
2x 1-1/2 PVC sch | https://www.homedepot.com/p/Charlotte-Pipe-1-1-2-in-PVC-Sch-40-S-x-S-Coupling-PVC021001400HD/203811389 | 3 | 2020-07-11 | 2.05 | 3
4x 1-1/2 45 deg bend | https://www.homedepot.com/p/Carlon-1-1-2-in-45-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA7AHB-CAR/100404155 | 13 | 2020-07-11 | 12.36 | 13
8x 90deg bend | https://www.homedepot.com/p/Carlon-1-1-2-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AHB-CTN/100404165 | 29 | 2020-07-11 | 28.17 | 29
21x 1-1/2 x 10ft | https://www.homedepot.com/p/JM-eagle-1-1-2-in-x-10-ft-PVC-Schedule-40-Conduit-67488/100140678 | 138 | 2020-07-11 | 137.84 | 138
Return of big pipe |  | -164 |  |  | -164
Gang Box | https://www.homedepot.com/p/Carlon-18-cu-in-Type-FSC-Gray-PVC-Electrical-Box-for-3-4-Conduit-E982EFN-CTN/100404109 | 7 | 2020-07-12 | 7 | 7
2x Box-gang 5 hole | https://www.homedepot.com/p/2-Gang-Weatherproof-Box-with-Five-3-4-in-Outlets-5345-0B/204208021 | 26 | 2020-07-12 | 26 | 26
Yello Wire Connector | https://www.homedepot.com/p/Commercial-Electric-Standard-Wire-Connectors-Yellow-30-Pack-778123/302686279 | 3 | 2020-07-12 | 3 | 3
Red Wire Connector | https://www.homedepot.com/p/Commercial-Electric-Standard-Wire-Connectors-Red-30-Pack-778124/302686275 | 3 | 2020-07-12 | 3 | 3
4x 3/4 male adapter | https://www.homedepot.com/p/3-4-in-Male-Terminal-Adapter-R5140104/202043511 | 2 | 2020-07-12 | 2 | 2
2x 90 deg elbow | https://www.homedepot.com/p/Carlon-3-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AEB-CTN/202304074 | 3 | 2020-07-12 | 3 | 3
1 Gang blank plastic cover | https://www.homedepot.com/p/BELL-1-Gang-Blank-Plastic-Cover-Gray-PBC100GYB/204125641 | 3 | 2020-07-12 | 3 | 3
3/4" x 10ft | https://www.homedepot.com/p/JM-eagle-3-4-in-x-10-ft-PVC-Schedule-40-Conduit-67454/100129197 | 4 | 2020-07-12 | 4 | 4
3x 3/4 x 10ft pvc | https://www.homedepot.com/p/JM-eagle-3-4-in-x-10-ft-PVC-Schedule-40-Conduit-67454/100129197 | 10 | 2020-07-18 | 9.46 | 10
3x 90 deg elbow | https://www.homedepot.com/p/Carlon-3-4-in-90-Degree-Schedule-40-PVC-Belled-End-Standard-Radius-Elbow-UA9AEB-CTN/202304074 | 4 | 2020-07-18 | 3.05 | 4
mini Patch Panel | https://www.amazon.com/gp/product/B00UVQI8B6/ref=ppx_yo_dt_b_asin_title_o01_s00?ie=UTF8&psc=1 | 23 | 2020-07-21 | 22.7 | 23
|  | 878 |  | Total | 878

## 13. Kid Labor
13. Kid Labor
Description | URLS | Estimate | Date | Amount | Amount Rounded Up
Moving Rock Away from darins |  | 60 |  | 60 | 60
Clearing rocks from yard and moving Amendment |  | 40 |  | 40 | 40
Rake Backyard |  | 10 |  | 10 | 10
Digging ditches /etc |  | 80 |  | 80 | 80
Corbin Digging |  | 40 |  | 40 | 40
Corbin Digging |  | 50 |  | 50 | 50
Kyndall Diggin |  | 30 |  | 30 | 30
Corbin Digging |  | 40 |  | 40 | 40
Corbin Weekend |  | 20 |  | 20 | 20
Kyndall Weekend |  | 20 |  | 20 | 20
Corbin Weekend |  | 40 |  | 40 | 40
Corbin/Kyndall rocks |  | 20 |  | 20 | 20
Corbin/Kyndall rocks |  | 40 |  | 40 | 40
Kid Labor |  | 510 |  |  | 0
|  | 1000 |  | Total | 490